## Budget Ref (hidden)
Main Categories
Administration
Capacity Building
Staffing
Project Expenses
| Sub-Categories | Main Categories
| Administrative Support Costs (OM) | Administration
| Capacity Building | Capacity Building
| Full Time Staff (35 hours or more per week) | Staffing
| Part Time Staff (less than 35 hours per week) | Staffing
| Transportation | Project Expenses
| Space | Project Expenses
| Honorarium (for participants, volunteers) | Project Expenses
| Support Services (translation, interpretation, child-minding) | Project Expenses
| Project Supplies and Materials | Project Expenses
| Project Equipment (rental or purchase) | Project Expenses
| Food | Project Expenses
| Fees (for services delivered) | Project Expenses
| Contingency | Project Expenses
| Other | Project Expenses

## Before you start
Youth Opportunities Fund
Definitions/Short Forms
FI:Family Innovations
YI: Youth Innovations
PGC: Parent, Guardians, Caregivers
The project plan and Budget template is for both the Youth Innovations and Family Innovations stream to use for groups to develop their application.
The project plan and Budget include example content to help you understand how to complete these templates.
Required Amounts
YI/FI Test - Annual amounts up to $100,000 per year, up to $300,000 for 3 years
YI/FI Scale - Annual amounts up to $150,000 per year, up to $450,000 for 3 years
TAKE NOTE: When entering your budget amount in the online application, the system will automatically round up your budget amounts. Be sure not to exceed total funding ceilings.

## Project Plan Example
The column titles for this worksheet are in rows 2, 3, and 7 through 8. They span cells A2, A3, and A7 through J8 inclusive. The following cells have Comments: none. The data spans cells A5 through J6, and A9 through J30. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
YOUTH OPPORTUNTIES FUND
Project Plan Example
Check one only. Year 1 Year 2 Year 3 | Select the type of activity from the list below: - Project Planning ¦ Prep Time - Recruitment ¦ Outreach - Resource Development - Training (Staff ¦ Volunteers) - Group Workshops ¦ Sessions - Drop in Time - Group Mentoring ¦ Coaching - Individual mentoring ¦ Coaching - Event ¦ Gathering - Ceremony - Partnership ¦ Networking - Doesn't Fit a Category | [5 empty] | Check resources that apply to the activity in this row. -Transportation - Space - Food - Honorarium - Support services (translation, child-minding, interpretation etc.) - Staff Time - Communications (website, promotions) - Volunteer Time - Project Supplies - Equipment - Other _____
Definitions/Short Forms FI:Famiily Innovations YI: Youth Innovations PGC: Parent, Guardians, Caregivers
YEAR | CATEGORY | WHAT ARE YOUR MAJOR ACTIVITIES? | WHEN WILL THE ACTIVITY TAKE PLACE? | WHAT IS THE FREQUENCY OF ACTIVITIES? | HOW MANY PEOPLE? (Family Innovations stream) | HOW MANY YOUTH? (Youth Innovations stream) | RESOURCES | OTHER DETAILS
In which year(s) will your activity take place? | Select the Type of Activity | List the major activities in your project: Use one row per activity List activities in the order they will occur. Include actions you will do to get ready to deliver your project and deliver for your groups. (Example: Design curriculum; Deliver workshop) | What month(s) of the year will this activity take place? | How often will the activity take place in a one year period? For example: weekly, monthly, once a year etc. | How many parents, guardians and/or caregivers do you expect will participate in this activity? | How may young people do you expect will participate in this activity? | Select the resources needed to complete this activity. | Add any notes or details about each activity that you are leading.
1 | Recruitment/Outreach | YI Example: Outreach to adult mentors/youth mentees across Brampton (all are Afro-Diasporic) starting with the organizations we know in our communities. FI Example: Outreach to parents, guardians and caregivers across Brampton (all are Afro-Diasporic). | August - September | 2 days per week during this period. | Not applicable | 10 | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
1 | Resource Development | YI Example: Design curriculum mentor-mentee gathering. In year 1, do a needs assessment, build a plan for the monthly sessions (topics / art forms we will use etc). | August - October | Not applicable | Not applicable | Not applicable | Staff Time Volunteer Time | Examples of other resources/curriculum
1 | Group workshops/sessions | YI Example: Group Workshop Activity: Deliver youth-mentor meet ups. We want to integrate storytelling and art into the format of the sessions. We will share a meal together. FI Example: Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - March | Twice a month week. Total 12 gatherings. | 10-15 women and their kids | 10 | Space Food Transportation Child-minding Honorarium Project Supplies
1 | Group Mentoring/Support | FI Example: Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families | 10 | Staff time StaffTransportation | Journals for each parent Coffee gift card for parents
1 | Individual Mentoring/Coaching | YI Example: One-to-One Mentoring: Youth-mentor pairs will meet on their own as well. The idea is that pairs will meet and can go deeper in their conversations and supports. | October - May | Once per month. Total 8 one on one meetings. | 10 | 10 | Transportation | Journals for each mentee Coffee gift card for each mentee
1 | Event ¦ Gathering | Annual Holiday Celebration (Year-end celebration). | December | Once per year | 30 | 30 | Space Food Transportation Equipment Project Supplies / decorations | Art supplies MC Sound System DJ Holiday cards
2 | Recruitment/Outreach | YI Example: Outreach to adult mentors and youth mentees (all are Afro-Diasporic). FI Example: Outreach to parents, caregivers and guardians across Brampton (all are Afro-Diasporic). We will aim to reach new neighbourhoods we haven't been active in before. | August - September | 2 days per week during this period. | 10 | 10 | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
2 | Resource Development | YI Example: Design curriculum mentor-mentee gathering. Update the plan each year based on the needs/interests of the new group of youth. FI Example: Refine and revise curriculum for parent and family support program based on feedback from Year 1. With information from a needs assessment - build a plan for the weekly sessions (topics, speakers, we will use etc). | June - August | Not applicable | Not applicable | Not applicable | Staff Time Volunteer Time | Examples of other program curriculum or workshop formats
2 | Group Workshops / Sessions | YI Example: Design curriculum mentor-mentee gathering. Update the plan each year based on the needs/interests of the new group of youth. FI Example: Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - May | Twice a month week. Total 12 gatherings. | 10-15 women and their kids |  | Space Food Transportation Child-minding Honorarium Project Supplies | Notebooks, pens, handouts Guest speakers
2 | Group Mentoring / Coaching / Support | YI Example: Group Mentoring Activity: Deliver youth-mentor meet ups. We want to integrate storytelling and art into the format of the sessions. We will share a meal together. This mentoring is happening in a group. FI Example: Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families |  | Transportation | Journals for each mentee Coffee gift card for each mentee
2 | Event / Gathering | Annual Holiday Celebration (Year-end celebration). | December | Once per year | 30 |  | Space Food Transportation Equipment Project Supplies | Art supplies MC Sound System DJ Holiday cards
3 | Recruitment / Outreach | YI Example: Outreach to adult mentors and youth mentees (all are Afro-Diasporic). FI Example: Outreach to parents, caregivers and guardians across Brampton (all are Afro-Diasporic). We will aiim to reach new neighbourhoods we haven't been active in before. | August - September | 2 days per week during this period. | 10 |  | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
3 | Resource Development | YI Example: Design curriculum mentor-mentee gathering. After final updates we will have a fully tested curriculum in place with a range of topics, resources and facilitator list. FI Example: Refine and revise curriculum for parent and family support program based on feedback from Year 1 and also with information from a needs assessment build a plan for the weekly sessions (topics / speakers we will use etc). | June - August | Not applicable | Not applicable |  | Staff Time Volunteer Time | Examples of other program curriculum or workshop formats
3 | Group Workshops/sessions | FI Example: Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - May | Twice a month week. Total 12 gatherings. | 10-15 women and their kids |  | Space Food Transportation Child-minding Honorarium Project Supplies | Notebooks, pens, handouts Guest speakers
3 | Group Mentoring / Support | YI Example: Group Mentoring Activity: Deliver youth-mentor meet ups. We want to integrate storytelling and art into the format of the sessions. We will share a meal together. This mentoring is happening in a group. FI Example: Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families |  | Transportation | Journals for each mentee Coffee gift card for each mentee
3 | Event / Gathering | Annual Holiday Celebration (Year-end celebration). | December | Once per year | 30 |  | Space Food Transportation Equipment Project Supplies | Art supplies MC Sound System DJ Holiday cards
3 | Resource Development | FI Example: Produce a final resource guide that features tips, contacts and tools for families. | April - February | Once in final year | 10 parents/guardians or caregivers |  | Staff Time Printing Honorarium | Updated Partner List Project Background Info Project Coordinator to lead
3 | Event / Gathering | FI Example: Invite all the progam participants for a release of the resource guide and invite community partners. | May | Once in final year | 35 families |  | Space Food Transportation Equipment | MC Sound System
3 | Resource Development | YI Example: Produce a final documentary that features our elders and youth experience. Interview youth-elders from every year of the project. | April - February | Once in final year | All youth participants from 3 years | All adult mentors from three years | Video-camera Editing Software (audio) Part-Time film maker Certificates
3 | Event ¦ Gathering | YI Example: Screen the documentary at a closing gathering. | May | Once in final year | All youth participants from 3 years |  | Space Food Transportation Equipment | MC Sound System

## Budget Worksheet Example
The column titles for this worksheet are in rows 2, 3, and 9. They span cells A2, A3, and B9 through I9 inclusive. The following cells have Comments: none. The data spans cells A5, B7 through I8, and A10 through I32. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
YOUTH OPPORTUNTIES FUND
Budget Worksheet Example
Complete the detailed budget request below. Use your Project Plan as a guide and try to capture all the expenses you will need.
| Select a category from the list: - Administration - Capacity Building (optional) - Staffing - Project Expenses | Choose an expense item from the list for the selected budget category: If "Administration" selected, choose from: - Administrative Support Costs (OM) If "Staffing" selected, choose from: - Full Time Staff (35 hours or more per week) - Part Time Staff (less than 35 hours per week) If "Project Expenses" selected, choose from: - Contingency - Transportation - Space - Honorarium (participants, volunteers) - Support Services (translation, interpretation, child-minding) - Project Supplies and Materials - Project Equipment (rental or purchase) - Food - Fees (for services delivered) - Other (specify in "Budget Notes") | Use this column to share more details or calculations about the expense on this line
Definitions/Short Forms FI: Family Innovations YI: Youth Innovations PGC: Parent, Guardians, Caregivers
| Budget Category | Expense Item | Budget Notes Use this space to show us how you calculated the amounts you are requesting. | Request Amount Year 1 | Request Amount Year 2 | Request Amount Year 3 | TOTAL
Required | Administrative | Administrative Support Costs (OM) | Formula: 15% of your total annual budget. | 10560 | 10560 | 9882.75 | 31100
Required | Capacity Building | YI and FI Stream: Capacity Building ($2,000 to $4,000) | $2,000 to $4,000 per year | 3000 | 3000 | 3000 | 9000
| Staffing | Part-Time Staff | $22 per hour x 30 hours x 52 weeks * 1.2 (Mandatory Employment Related Costs) | 41184 | 41184 | 41184 | 123600
| Staffing | Part-Time Staff | $22 per hour x 10 hours x 30 weeks * 1.2 (Mandatory Employment Related Costs) | 7920 | 7920 | 7920 | 23800
| Project Expenses | Project Supplies and Materials | Design and print flyers for outreach to families and community partners | 1000 | 1000 | 1000 | 3000
| Project Expenses | Transportation | Staff and facilitator transportation for meetings, outreach etc. | 250 | 250 | 250 | 800
| Project Expenses | Transportation | For participants: 12 meetings x 15 families (round trip) | 1980 | 1980 | 1980 | 6000
| Project Expenses | Space | Monthly meeting space and training space = $150 per meeting x 12 meetings | 1200 | 1200 | 1200 | 3600
| Project Expenses | Supplies | Honorariums and supplies for bi-monthly meet ups. About $150 per monthly session. | 1800 | 1800 | 1800 | 5400
| Project Expenses | Project Supplies and Materials | Coffee cards for neighbourhood support meetings valued at $20 (15 participants x $20 per card). See project worksheet for more details. | 300 | 300 | 300 | 900
| Project Expenses | Food | Bi-monthly meetings. $6 per person x 30 participants + 3 staff/facilitators | 2376 | 2376 | 2376 | 7200
| Project Expenses | Food | Annual celebration event $15 per person X 35 people | 525 | 525 | 525 | 1600
| Project Expenses | Space | Rental space for annual celebration | 200 | 200 | 200 | 600
| Project Expenses | Fees (for services delivered) | Fees for Celebration Event - DJ and MC | 500 | 500 | 500 | 1500
| Project Expenses | Equipment (rental or purchase) | Rent sound system for celebration event | 200 | 200 | 200 | 600
| Project Expenses | Space | Closing Event and Resource handbook release | 800 | 800 | 800 | 2400
| Project Expenses | Honorarium | 1 guest facilitator for every session ($100 x 12) | 800 | 800 | 800 | 2400
| Project Expenses | Printing | Printing of resource handbook, one copy per participant / family |  |  | 800 | 800
| Project Expenses | Equipment (rental or purchase) | Rent projector and screen and sound system |  |  | 800 | 800
| Project Expenses | Contingency | up to 10% of your total annual budget | 5632 | 5632 |  | 11300
| TOTAL YOF BUDGET REQUEST |  |  | 80227 | 80227 | 75517.75 | 236400
TIP! Watch your annual funding ceiling. Test ceiling is $100,000 per year Scale ceiling is $150,000 per year